# CONTRACTUAL AGREEMENT

Between

THE CENTRAL SAVANNAH RIVER AREA REGIONAL COMMISSION

(hereafter referred to as “RC”) and

WASHINGTON COUNTY AND THE CITIES OF SANDERSVILLE, TENNILLE, DEEPSTEP, DAVISBORO, OCONEE, RIDDLEVILLE, AND HARRISON

(hereafter referred to as “CONTRACTING AGENCIES”)

PROJECT NAME

## Washington County Joint Comprehensive Plan 2026-2031

| For Official Use Only: |  |  |
| --- | --- | --- |
| Effective Date: | Expiration Date: | Contract Number: |

SECTION 1 – SCOPE OF SERVICES

The CONTRACTING AGENCIES agree to engage the services of the RC and, the RC agrees to perform those services established in ATTACHMENT A.

# SECTION 2 – EXPECTATIONS OF THE CONTRACTING AGENCIES

The RC’s provision of services is contingent upon the assistance of the CONTRACTING AGENCIES as provided in ATTACHMENT A.

# SECTION 3 – MILESTONES AND PROJECT SCHEDULE

Upon written notice of award, the RC will begin work as outlined in ATTACHMENT A. All work performed by the RC shall be in accordance with the schedule established in ATTACHMENT B. This contract shall expire on the 28th day of February, 2026.

# SECTION 4 – COMPENSATION

The RC will devote sufficient staff to the project with the capabilities and expertise to complete the project. The RC will prepare interim bills – if applicable - as the work progresses based on the milestones and project schedule established in ATTACHMENT B.

The total amount of payments to be paid by the CONTRACTING AGENCIES to the RC for work performed under this contract shall be at no cost; except, that additional services mutually agreed upon in writing by both parties may be billed at an additional and applicable hourly rate of the RC staff member(s), performing the service.

# SECTION 5 – METHOD OF PAYMENT

Amounts for RC services provided outside of the scope of ATTACHMENT A will be billed by the RC on an ongoing basis. Payment is expected within thirty (15) working days of receipt of an invoice.

# SECTION 6 - OWNERSHIP

All data, reports, maps, or other deliverables produced in whole or in part under this contract shall remain the property of the CONTRACTING AGENCIES. Furthermore, the RC will not apply for a copyright for any reports, data, or other documents produced in whole or in part under this agreement.

# SECTION 7 - RC’S RELATIONSHIP TO THE CONTRACTING AGENCIES

It is expressly agreed and understood that the RC is in all respects an independent Contractor as to work and is in no respect any agent, servant, or employee of the CONTRACTING AGENCIES. The contract specifies the work to be done by the RC, but the method to be employed to accomplish the work shall be the responsibility of the RC.

The RC will disclose, to the CONTRACTING AGENCIES, prior to signing of this Agreement, the identity of any and all subcontractors to be used in the performance of this contract. Should the need arise, during the performance of this Agreement, for the RC to subcontract any services not previously identified, it may do so, but only with the prior approval of the CONTRACTING AGENCIES, which approval shall not be unreasonably withheld. No such approval will be construed as making the CONTRACTING AGENCIES a part of, or to, such subcontract, or subjecting the CONTRACTING AGENCIES to liability of any kind to any subcontractor. No subcontract shall, under any circumstances, relieve the RC of its liability and obligation under this contract; and despite any such subcontracting the CONTRACTING AGENCIES shall deal through the RC, and subcontractors will be dealt with as representatives of the RC.

The RC shall not assign or transfer, whether by an assignment or novation, any of its rights, duties, benefits, obligations, liabilities, or responsibilities under this Contract without the written consent of the CONTRACTING AGENCIES; provided, however, that assignments to banks, trust companies, or other financial institutions for the purpose of securing bond may be made without the consent of the CONTRACTING AGENCIES. Assignment or Novation of this Contract shall not be valid unless the Assignment or Novation expressly provides that the assignment of any of the RC’s rights or benefits under the Contract is subject to a prior lien for labor performed, services rendered, and materials, tools, and equipment supplied for the performance of the work under this contract in favor of all persons, firms, or corporations rendering such labor or services or supplying such materials, tools, and equipment.

# SECTION 8 - EQUAL EMPLOYMENT OPPORTUNITY

During the performance of this contract, RC agrees as follows:

The RC will not discriminate against any employee or applicant for employment because of race, religion, color, sex, or national origin, except where religion, sex, or national origin is a bona fide occupational qualification reasonably necessary to the normal operation of RC. RC agrees to post in conspicuous places, available to employees or applicants for employment, notices setting for the provisions of this nondiscrimination clause.

The RC also shall not discriminate against any handicapped person in violation of any state or federal law or regulation and shall also post in conspicuous places, available to employees and applicants for employment, notices setting the provisions of this additional nondiscrimination clause.

The RC, in all solicitations or advertisements for employees placed by or on behalf of RC, will state that such contractor is an equal opportunity employer.

Notices, advertisements and solicitations placed in accordance with federal law, rule or regulation shall be deemed sufficient for the purpose of meeting the requirements of this selection.

The RC will otherwise comply with all other applicable provisions of local, State and Federal law.

# SECTION 9 - DRUG AND SMOKE-FREE WORKPLACE

The RC hereby certifies that it will not engage in the unlawful manufacture, sale, distribution, possession, or use of a controlled substance or marijuana during the performance of this Agreement. The RC may be suspended, terminated, or debarred if it is determined that:

- The RC has made false certification herein above; or

- The RC has violated such certification by failure to carry out the requirements of Official Code of Georgia 50- 24-3.

# SECTION 10 - CONFIDENTIALITY

To the extent permitted by law, all data and information gathered by the RC and any of its Subcontractors, and all reports, recommendations, drawings, specifications, photographs, and data shall be treated by the RC and its Subcontractors as confidential. Once all final deliverables are received and accepted by the CONTRACTING AGENCIES, all information contained therein will be treated as public information.

The CONTRACTING AGENCIES and the RC mutually agree not to use each other’s name, either expressly or by implication, in any of their advertising or sales materials or public notices without prior written agreement.

The CONTRACTING AGENCIES retain all title and interest to the data and any reports associated with the Agreement.

# SECTION 11 - TERMINATION FOR CAUSE

If, through any cause, the RC shall fail to fulfill in a timely and proper manner its obligation under this agreement, or if the RC shall violate any of the covenants, agreements, or stipulations of this agreement, the CONTRACTING AGENCIES shall have the right to terminate this agreement by giving written notice to the RC of such termination and specifying the effective date thereof, at any time, at least thirty (30) days prior to the effective date of such termination. In that event, all finished or unfinished documents, data, or other materials as described in Section 1 - Scope of Services, shall become the property of the CONTRACTING AGENCIES. The CSRA RC shall be entitled to receive just and equitable compensation for any satisfactory work completed and any outstanding obligations on such documents. Also, the CONTRACTING AGENCIES shall be entitled to receive a pro-rated refund of payment for any work not complete at time of termination.

# SECTION 12 - TERMINATION FOR THE CONVENIENCE OF THE RC

If through any cause, the CONTRACTING AGENCIES shall fail to fulfill in a timely and proper manner its obligations under this agreement, or if the CONTRACTING AGENCIES shall violate any of the covenants, agreements, or stipulations of this agreement, the RC shall have the right to terminate this agreement by giving written notice to the CONTRACTING AGENCIES of such termination and specifying the effective date thereof, at any time, at least (30) days prior to the effective date of such termination. In that event, all finished or unfinished documents, data, or other materials as described in Section 1 – Scope of Services, shall become the property of the CONTRACTING AGENCIES. The RC shall be entitled to receive just and equitable compensation for any satisfactory work completed and any outstanding obligations on such documents. Also, the CONTRACTING AGENCIES shall be entitled to receive a pro-rated refund of payment for any work not complete at time of termination.

# SECTION 13 - LIMITATION OF LIABILITY

If the RC, its employees or agents, fail for any reason, whether or not negligent, to fulfill the conditions as contained in this contract, the CONTRACTING AGENCIES remedy shall be to receive a refund of all monies paid for the Project.

# SECTION 14 - COMPLIANCE WITH LAWS, RULES, AND REGULATIONS

The RC, its officers, agents, employees, and subcontractors, in the performance of this Agreement shall comply with all applicable statutes and laws of the United States and the State of Georgia, and the applicable rules and regulations of the agencies of the United States and the State of Georgia.

# SECTION 15 - CONFORMANCE OF AGREEMENT WITH THE LAW

It is the intent and understanding of the parties to this Agreement that each and every provision of law required to be inserted in this Agreement shall be and is inserted herein. Furthermore, it is hereby stipulated that every such provision is deemed to be inserted herein, and if through mistakes or otherwise, any such provision is not inserted in correct form, then this Agreement shall upon application of either party, be amended by such insertion so as to comply strictly with the law and without prejudice to the rights of either party.

If this Agreement contains any unlawful provisions, not an essential part of the Agreement and which appears not to have been a controlling or material inducement to the making hereof, the same shall be deemed of no effect, and shall upon the application of either party be stricken from the Agreement without affecting the binding force of the Agreement as it shall remain after omitting such provision. The parties agree that this Agreement shall be reformed to replace such stricken provision or part thereof with a valid and enforceable provision which comes as close as possible to expressing the intention of the stricken provision.

# SECTION 16 - ENFORCEMENT

This Agreement and the performance hereof shall be governed by and enforced under the laws of the State of Georgia, and if legal action by either party is necessary for or with respect to the enforcement of any or all of the terms and conditions hereof, then exclusive venue therefore shall lie in Richmond County, Georgia.

# SECTION 17 - NOTICES

All written notices required to be given by the RC to the CONTRACTING AGENCIES shall be electronically delivered or addressed and mailed or hand delivered to:

| Mr. Horace Daniels, Chairman Washington County Board of Commissioners C/O: Christ Hutchings, County Administrator 119 Jones Street Sandersville, GA 31082 | Mayor Valerie Brown City of Davisboro C/O: ShaQuetta Brown, City Manager P.O. Box 189 Davisboro, GA 31018 | Mayor James Pittman City of Oconee C/O: Regina Freeman, City Clerk P.O. Box 69 Oconee, GA 31067 | Mayor Ken Westbrook City of Riddleville 225 Jennie Lee Poole Rd Harrison, GA 31035 |
| --- | --- | --- | --- |
| Mayor Eartha Cummings City of Tennille C/O: Stacy Jordan, City Clerk P.O. Box 145 Tennille, GA 31089 | Mayor Randall Veal Town of Deepstep C/O: Dorenda Smith, City Clerk 9376 Deepstep Road Sandersville, GA 31082 | Mayor Joe Walker Town of Harrison C/O: Sarah Anderson, City Clerk P.O. Box 31 Harrison, GA 31035 | Mayor James Andrews City of Sandersville C/O: David Larson, Community Development Director P.O. Box 71 Sandersville, GA 31082 |

All such notices required to be given by the CONTRACTING AGENCIES to the RC shall be addressed and mailed or delivered to Andy Crosson, Executive Director, CSRA Regional Commission, 3626 Walton Way Extension, Suite 300, Augusta, GA 30909.

# SECTION 18 - SUCCESSORS; ASSIGNMENT

The CONTRACTING AGENCIES and the RC respectively bind themselves, their partners, successors, assigns, and legal representatives, to the other with respect to all covenants and agreements herein contained and made. Neither the CONTRACTING AGENCIES nor the RC shall, however, assign or transfer any of its interest in or rights or obligations under this Agreement without the prior written consent of the other.

# SECTION 19 - EXHIBITS; ENTIRE AGREEMENT; AMENDMENTS

This Agreement represents the entire Agreement between the CONTRACTING AGENCIES and the RC and supersedes all prior negotiations, representations, agreements, and understandings, written, or oral, made by either or both with respect to this Agreement and Project.

The terms, conditions, and provisions of this Agreement may be modified, amended, supplemented, deleted, or canceled only with the consent of and by prior written instrument duly signed by both CONTRACTING AGENCIES and the RC.

IN WITNESS WHEREOF, the CONTRACTING AGENCIES and the RC have each caused this Agreement to be signed and sealed in its behalf, by its duly authorized officers or principals, in two (2) original counterparts, each of which counterparts shall be deemed the original Agreement without the need to account for the other and all of which counterparts together shall constitute but one and the same Agreement.

# SECTION 20 - REVIEW BY LEGAL REPRESENTATION

All new products, policies, procedures, ordinances, or regulations generated under this contract and/or any revisions or alterations to existing policies, procedures, ordinances, regulations, etc… should be reviewed and approved by legal counsel for the CONTRACTING AGENCIES prior to adoption by the CONTRACTING AGENCIES. A letter of opinion from the CONTRACTING AGENCIES’ legal counsels outlining the applicable legal counsel’s opinion of the final document and/or any process used to adopt such document(s) is strongly recommended by the RC, and a copy of such opinion is requested through this contract for the RC’s files. Legal counsel’s opinion letter is to be obtained at the CONTRACTING AGENCIES’ expense. The RC assumes no liability for subsequent legal action taken against the CONTRACTING AGENCIES as it relates to this project.

# SECTION 21 - AMENDMENTS/MODIFICATIONS

From time to time, the CONTRACTING AGENCIES and the RC may mutually consent to changes in the Section 1 - Scope of Services, Section 3 – Milestones and Project Schedule, or any other aspect of this agreement. Such changes, including any increases or decreases in the compensation paid to the RC, shall be incorporated in written amendments to this agreement and signed by the duly authorized representatives of all parties.

This agreement may be modified only by a formal, written modification signed by authorized representatives of the CONTRACTING AGENCIES and the RC. All changes to the Scope of Services, Milestones and Payment Schedule and/or any other aspect of this agreement shall be agreed upon and mutually accepted via contract amendments executed by the CONTRACTING AGENCIES and the RC.

# SECTION 22 - RIGHT TO AUDIT

The RC agrees to give the CONTRACTING AGENCIES, through any authorized representative, the right to audit all records, books, papers, or documents related to the agreement for up to three (3) calendar years after completion of this agreement.

# SECTION 23 - ACCEPTANCE OF CONTRACT AND TERMS

This Agreement shall become effective with the signatures of the authorized parties and shall remain in effect until both parties shall agree that the services have been performed. Any revisions to the deadline date for the completion of the work shall be mutually agreed upon in writing by both parties.

This Agreement, entered into by and between the parties whose signatures appear below, representing their respective organizations, this 	day of 	, 	.

| ________________________________ Horace Daniels, Chairman Washington County Board of Commissioners ________________________________ Date ________________________________ Witness | ________________________________ Valerie Brown, Mayor City of Davisboro ________________________________ Date ________________________________ Witness |
| --- | --- |
| ________________________________ James Pittman, Mayor City of Oconee ________________________________ Date ________________________________ Witness | ________________________________ Ken Westbrook, Mayor City of Riddleville ________________________________ Date ________________________________ Witness |
| ________________________________ Eartha Cummings, Mayor City of Tennille ________________________________ Date ________________________________ Witness | ________________________________ Randall Veal, Mayor Town of Deepstep ________________________________ Date ________________________________ Witness |

This Agreement, entered into by and between the parties whose signatures appear below, representing their respective organizations, this 	day of 	, 	.

| ________________________________ Joe Walker, Mayor Town of Harrison ________________________________ Date ________________________________ Witness | ________________________________ James Andrews, Mayor City of Sandersville ________________________________ Date ________________________________ Witness |
| --- | --- |
| ________________________________ Andy Crosson, Executive Director CSRA Regional Commission ________________________________ Date ________________________________ Notary |  |

# ATTACHMENT A SCOPE OF SERVICES

## (Washington County Comprehensive Plan 2021-2026)

The “scope of services” establishes the specific tasks and products which will be provided by the Central Savannah River Area Regional Commission (RC) staff to the CONTRACTING AGENCIES. Any tasks or products sought by the CONTRACTING AGENCIES from the RC which are in addition to those outlined herein must be agreed to in writing by the authorized parties representing their respective agencies, and as referenced in Section 21 – Amendments/Modifications of the contract.

# Task #1: Comprehensive Plan Update.

RC staff will prepare a Washington County Comprehensive Plan 2021-2026 document for the CONTRACTING AGENCIES adhering to, and exceeding, Chapter 110-12-1 of the Rules of the Georgia Department of Community Affairs (the “Minimum Standards and Procedures for Local Comprehensive Planning;” effective date: October 1, 2018.) In preparing the document, all plan elements required by the state of Georgia, and applicable to the jurisdiction of the CONTRACTING AGENCIES, and additional topics shall be incorporated into the final product including the following:

Community Goals

Needs and Opportunities Community Work Program Broadband Services Economic Development Land Use

Community Facilities

Natural and Cultural Resources Housing

Task #2: Service Delivery Strategy Update.

RC staff may prepare, in conjunction with its comprehensive planning work referenced within Task #1, a new Joint Service Delivery Strategy (SDS) for the CONTRACTING AGENCIES in accordance with the applicable standards and provisions of O.C.G.A. § 36-70-20 et.seq. (Article 2. Service Delivery.)

# Public Meetings and Hearings:

  - RC staff shall accomplish the tasks referenced within this ATTACHMENT primarily in conjunction with a joint stakeholder advisory committee whose representation shall be agreed to by the chief elected officials of the CONTRACTING AGENCIES.

  - RC staff will prepare for, attend, and facilitate a minimum of four (2) stakeholder committee meetings throughout the course of the planning project.

  - RC staff may prepare for, attend, and facilitate additional stakeholder meetings and public input sessions (including an open house) deemed necessary and agreed to by both the CONTRACTING AGENCIES and RC staff.

  - RC staff may prepare for, attend, and facilitate additional meetings the CONTRACTING AGENCIES on a request, and subject to the convenience, and joint agreement of, both the requesting CONTRACTING AGENCIES and RC staff.

# Interim Products:

RC staff will provide the CONTRACTING AGENCIES with draft documents throughout the comprehensive planning and service delivery strategy update process as necessary to ensure ongoing consistency with the scope of this proposal. The preparation and distribution of interim documentation shall be based on the schedule and parameters established in ATTACHMENT B (MILESTONES AND PROJECT SCHEDULE.)

# Final Products:

RC staff will provide the CONTRACTING AGENCIES with one (1) digital and ten (1) hard copies of a final comprehensive plan document, and one (1) digital and one (1) hard copy of a final service delivery strategy document (if an agreement is reached during the process). Final digital products will be generated utilizing Adobe programs and shall be provided by the RC to the CONTRACTING AGENCIES in a format suitable for their internal use and reproduction. All final products represent a recommendation on behalf of the RC and final adoption and approval will be at the discretion of the CONTRACTING AGENCIES.

# Expectations of the CONTRACTING AGENCIES:

  - The CONTRACTING AGENCIES will advertise and conduct all public hearings required by Chapter 110-12-1 of the Rules of the Georgia Department of Community Affairs (the “Minimum Standards and Procedures for Local Comprehensive Planning;” effective date: October 1, 2018).

  - The CONTRACTING AGENCIES will provide the RC with contact information for all stakeholder committee members.

  - The CONTRACTING AGENCIES will meet with RC staff as provided within this ATTACHMENT, and ATTACHMENT B; and, as necessary to address unforeseen issues that may arise while implementing this agreement.

  - The CONTRACTING AGENCIES will coordinate, attend and assist all meetings referenced in this ATTACHMENT; and, accept financial responsibility for all public advertising costs.

  - The CONTRACTING AGENCIES will review and comment on draft documents provided by RC staff within a reasonable timeframe as established in ATTACHMENT B.

  - The CONTRACTING AGENCIES will cause the final products identified within this ATTACHMENT to be reviewed and approved by an attorney, as well as any associated documents or recommended adoption procedures generated by the RC.

  - The CONTRACTING AGENCIES will assist the RC in the compilation of data sets necessary to sufficiently complete the final products identified within this ATTACHMENT.

# ATTACHMENT B MILESTONES AND PROJECT SCHEDULE

## (Washington County Comprehensive Plan 2021-2026)

The “Milestones and Project Schedule” establishes the timeframe in which Central Savannah River Area Regional Commission (RC) staff and the CONTRACTING AGENCIES will conduct those activities referenced in ATTACHMENT A “Scope of Services”. Milestones referenced herein are approximate. The schedule is ultimately a guide and is subject to substantial modification throughout the planning process upon the joint agreement of the CONTRACTING AGENCIES and RC staff.

| Milestone | Task | Notes | Date |
| --- | --- | --- | --- |
| 1. | First public hearing | Required component. | 4/2025 |
| 2. | Stakeholder committee meeting #1 | Overview of required planning initiatives; SWOT exercise. | 5/2025 |
|  | Community Involvement | Required component. Throughout the process – sharing info online or in community buildings, making draft documents available, soliciting feedback via surveys/emails/conversations, etc. | Ongoing |
| 3. | Stakeholder committee meeting #2 | Review of existing goals, policies, and needs/opportunities. | 06/2025 |
| 4. | Stakeholder committee meeting #3 | Data & Plan elements. | 08/2025 |
|  | Review and update of work programs | Stakeholder review of previous community work program, completion of Report of Accomplishments, and drafting of new work program items. | Ongoing |
| 5. | Stakeholder committee meeting #4 | Data & Plan elements. | 09/2025 |
| 6. | Stakeholder committee meeting #5 | Review of draft community work program. | 10/2025 |
| 7. | Joint SDS Meeting | See Description within Task #2 of Attachment A. | TBD |
| 8. | Stakeholder committee meeting #6 | Draft document review. | 11/2025 |
| 9. | CONTRACTING AGENCIES holds a second public hearing and submit plan to Georgia DCA for review. | Required component. | 12/2025 |
| 10. | Final products adopted by CONTRACTING AGENCIES and approved by Georgia DCA. | Official action by CONTRACTING AGENCIES. | 1/2026 |
| 11. | Final products to CONTRACTING AGENCIES. | Final draft Comprehensive Plan document | 2/2026 |